## Summary
STRADA INTELLIGENCE — BUG TRACKER SUMMARY
Total Bugs Logged | 1
Open (not closed/rejected) | 1
Closed / Verified | 0
Avg Days Open | 0
By Status | Count | By Priority | Count
New | 0 | P0 - Critical | 0
Triaged | 1 | P1 - High | 0
In Progress | 0 | P2 - Medium | 1
Blocked | 0 | P3 - Low | 0
In Review | 0
Fixed - Pending Verification | 0 | By Dashboard Section | Count
Verified / Closed | 0 | 1. Verdict / Headline Score | 0
Reopened | 0 | 2. KPI Tiles | 0
Won't Fix | 0 | 3. Seven Pillars | 0
Duplicate | 0 | 4. Property Mix | 0
Cannot Reproduce | 0 | 5. 9-Month Trend Charts | 0
|  | 6. Asking Price Per Sq Ft | 0
|  | 7. Transaction Volume by Area | 0
|  | 8. Rental Yield by Property Type | 0
|  | 9. Recent Sales Transactions | 0
|  | Global / Site-wide (header, nav, layout) | 0
|  | Data Pipeline / Backend | 0

## Bug Log
STRADA INTELLIGENCE — WEBSITE BUG TRACKER
Log every bug — large or small. Use the dropdowns to keep categories consistent for the review team. New rows auto-extend the table.
Bug ID | Date Reported | Reported By | Status | Priority | Severity | Title / Summary | Dashboard Section | Bug Category / Type | Affected Data Source | Environment | Browser / Device | Steps to Reproduce | Expected Result | Actual Result | Frequency | Screenshot / Link | Assigned To | Date Resolved | Days Open | Root Cause | Resolution / Notes
BUG-001 | 22/06/2026 | Kyle | Triaged | P2 - Medium | S3 - Major | Total listing volume for rent is showing an abnormally large number for Jumeirah Village Circle (28020 listings) which could suggest file dump is not de duping. I manually checked on propertyfinder and this many listings did not come up. | 10.Lising volume | Data Accuracy (wrong value) | Property Portal Data | Development | Chrome 126 / Desktop | 1. Open dashboard. 2. View Listing data | Figure should be around 15,000 or 18,000 | Tile reads around 28,000 | Always (100%) |  | Data Team |  | #VALUE! |  | Suspect currency aggregation dropping AED-denominated rows.
Formulas:
Days Open = IF(BugLog[[#This Row],[Date Reported]]="","",IF(BugLog[[#This Row],[Date Resolved]]="",TODAY()-BugLog[[#This Row],[Date Reported]],BugLog[[#This Row],[Date Resolved]]-BugLog[[#This Row],[Date Reported]]))

## Lists
Status | Priority | Severity | Dashboard Section | Bug Category / Type | Affected Data Source | Environment | Frequency
New | P0 - Critical | S1 - Blocker | 1. Verdict / Headline Score | Data Accuracy (wrong value) | DLD Transactions | Production | Always (100%)
Triaged | P1 - High | S2 - Critical | 2. KPI Tiles | Data Freshness / Stale Data | Rental Yield Data | Staging | Often
In Progress | P2 - Medium | S3 - Major | 3. Seven Pillars | Missing / No Data | Asking Prices | Development | Sometimes
Blocked | P3 - Low | S4 - Minor | 4. Property Mix | Calculation / Logic Error | Oil / Brent Price |  | Rarely
In Review |  | S5 - Cosmetic | 5. 9-Month Trend Charts | Chart / Visualization | Interest Rates |  | Once
Fixed - Pending Verification |  |  | 6. Asking Price Per Sq Ft | UI / Layout / Styling | Stock Markets (UAE / Gulf)
Verified / Closed |  |  | 7. Transaction Volume by Area | Functional / Broken Feature | News / Geopolitics Feed
Reopened |  |  | 8. Rental Yield by Property Type | Navigation / Broken Link | Tourism / Aviation Data
Won't Fix |  |  | 9. Recent Sales Transactions | Performance / Slow Load | Developer Financials
Duplicate |  |  | 10.Lising volume | Responsive / Mobile | Multiple / Mixed
Cannot Reproduce |  |  | Global / Site-wide (header, nav, layout) | Accessibility | N/A (UI only)
|  |  | Data Pipeline / Backend | Content / Copy / Label | Property Portal Data
Data Source / API Integration
Security
Other